## project
[8 empty] | Week 1 |  |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
[40 empty] | Altium Component Library Review | [13 empty] | Schematic Review |  |  |  |  | Demo IDE Running |  | Layout Review |  |  | Midterm |  |  |  | Final Design Review | [6 empty] | PCB released to fab |  | Spring Break Week | [6 empty] | PCB back for assembly | [6 empty] | Assembly Complete | [21 empty] | Midterm2 (Final) | [6 empty] | Project Demos
Project Planner
[8 empty] | Day Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  |  | Actual (beyond plan)
[20 empty] | % Complete |  |  |  |  | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | January 11th | [5 empty] | January 17th | [6 empty] | January 24th | [7 empty] | February 1st | [5 empty] | February 7th | [6 empty] | February 14th | [7 empty] | February 22nd | [6 empty] | March 1st | [30 empty] | April 1st | [28 empty] | Finals Week | May1st
ACTIVITY |  | START | DURATION | START | DURATION | COMPLETE |  | Days
| Lead | [5 empty] | Comments | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116
Finalize project team | Saloni, Rajat | 1 | 5 | 2 | 4 | 100%
Finalize product idea | Saloni, Rajat | 8 | 3 | 9 | 3 | 100%
Select sensor | Saloni, Rajat | 8 | 3 | 9 | 3 | 100%
Select encoder-wheel assembly | Saloni | 16 | 2 | 16 | 2 | 100%
Select graphic LCD | Rajat | 16 | 2 | 16 | 3 | 100%
Estimate total power cconsumption | Saloni | 17 | 3 | 17 | 3 | 100%
Load power management | Rajat | 17 | 3 | 18 | 2 | 100%
Analyzing interface of sensors | Rajat | 17 | 2 | 18 | 2 | 100%
Finalize battery | Saloni, Rajat | 23 | 3 | 24 | 2 | 100%
Study voltage regulator Ics | Saloni, Rajat | 22 | 4 | 23 | 4 | 100%
Finalize Solar Panel | Rajat | 29 | 1 | 30 | 2 | 100%
Interface LCD Display with Blue Gecko | Saloni, Rajat | 34 | 3 | 35 | 3 | 100%
Altium Component Library List | Saloni, Rajat | 30 | 3 | 29 | 3 | 100%
Finalize bulk capacitance | Rajat | 33 | 2 | 37 | 3 | 100%
Schematic for power management | Saloni | 34 | 3 | 0 | 0 | 0% | To be completed next week
Schematic for sensor interfacing | Rajat | 44 | 3 | 0 | 0 | 0%
Interfacing IMU sensor with Blue Gecko | Saloni | 44 | 3 | 0 | 0 | 0%
Final schematic integration | Saloni, Rajat | 46 | 2 | 0 | 0 | 0%
Demo IDE finalize | Saloni, Rajat | 49 | 3 | 0 | 0 | 0%
Complete layout of the product | Saloni, Rajat | 52 | 2 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%